Project Title: Adaptive Hybrid VEM-Deep Learning for Two-Dimensional Structural Problems with Uncertainty Estimation and PINN Comparison

Objective

This project aims to develop an adaptive hybrid Virtual Element Method (VEM) - Deep Learning (DL) approach for solving two-dimensional structural mechanics problems under the Theory of Linear Elasticity. The study will focus on implementing uncertainty-aware adaptive refinement strategies, extending the hybrid method to more complex 2D structural systems, and comparing the approach with Physics-Informed Neural Networks (PINNs) to assess its advantages and limitations.

Motivation

Traditional numerical methods such as Finite Element Method (FEM) and Virtual Element Method (VEM) require computationally expensive meshing and numerical system solutions, especially for high-resolution problems. Deep Learning offers the potential for fast inference, but its accuracy and generalization depend on data availability and the training process. By combining these methods, the hybrid VEM-Deep Learning approach aims to preserve the accuracy of VEM while leveraging the speed of deep learning inference, making it particularly relevant for adaptive mesh refinement strategies and real-time structural analysis. Furthermore, uncertainty estimation can help refine the mesh where the neural network lacks confidence, improving computational efficiency.

Research Plan

The project will be divided into three interconnected phases:

Phase 1: Adaptive Refinement Strategies for Hybrid VEM-Deep Learning

Goal

Develop a self-adaptive hybrid VEM-Deep Learning framework that dynamically refines the mesh based on model uncertainty.

Key Steps

1.	Uncertainty Quantification:

•	Implement Bayesian Deep Learning (e.g., Monte Carlo Dropout) to estimate model uncertainty.

•	Analyze confidence intervals in the displacement field predictions.

2.	Adaptive Mesh Refinement:

•	Define an error metric based on uncertainty estimates to refine the VEM mesh adaptively.

•	Implement an iterative refinement process, where the mesh is refined in regions where the neural network has high uncertainty or large prediction errors.

3.	Performance Evaluation:

•	Compare computational cost and accuracy of the adaptive model vs. fixed-resolution hybrid and pure VEM approaches.

•	Assess whether the uncertainty-aware refinement improves the model’s efficiency and robustness.

Expected Outcome

A hybrid model that balances computational efficiency and accuracy by refining only where necessary, reducing the computational cost of high-resolution VEM simulations.

Phase 2: Application to Complex 2D Structural Systems

Goal

Extend the hybrid VEM-Deep Learning approach to analyze two-dimensional structural problems, moving beyond simple beam/portic geometries.

Key Steps

1.	Problem Selection:

•	Focus on plane stress/plane strain problems, including trusses, frames, and shell structures.

•	Consider both homogeneous and heterogeneous materials.

2.	Deep Learning for Complex Structures:

•	Train the model using VEM-generated datasets to approximate displacement fields efficiently.

•	Investigate the role of data-driven material models for predicting material heterogeneity.

3.	Comparison with Classical Methods:

•	Evaluate the performance of the hybrid approach against traditional high-order VEM solutions.

•	Measure accuracy, convergence behavior, and computational cost.

Expected Outcome

A generalized hybrid approach applicable to a broader range of 2D structural problems, showcasing its adaptability to complex geometries and materials.

Phase 3: Comparison with Physics-Informed Neural Networks (PINNs)

Goal

Compare the hybrid VEM-Deep Learning approach with Physics-Informed Neural Networks (PINNs) to determine their respective strengths and weaknesses.

Key Steps

1.	Implement a PINN Model:

•	Solve the linear elasticity equations using a PINN trained to satisfy the governing equations and boundary conditions.

•	Compare PINNs trained with data vs. purely physics-based PINNs.

2.	Performance Metrics:

•	Compare error convergence, computational efficiency, and generalization between PINNs and the hybrid model.

•	Analyze cases where PINNs perform well vs. where the hybrid approach is superior.

3.	Assessment of Practical Use Cases:

•	Identify scenarios where PINNs are beneficial, such as cases with limited data but strong physics priors.

•	Highlight when the hybrid model outperforms PINNs, such as for large-scale problems requiring efficient inference.

Expected Outcome

A comparative study outlining the strengths and weaknesses of PINNs vs. the hybrid VEM-Deep Learning approach, providing valuable insights for future research in data-driven numerical methods.